## Burndown Table
BURNDOWN TABLE ¦ ERROR 404
Week # | Work Date | Planned work remaing (hours) | Planned effort (hours) | Actual work remaining(hours) | Actual work done(hours) | Description
1 | 2016-02-04 | 80 | 5 | 80 | 0 | Introduction to project work requirements and specification
2 | 2016-02-11 | 75 | 5 | 78 | 2 | Gathered information and hypothesised about our chosen topic
3 | 2016-02-18 | 70 | 5 | 74 | 4 | corrected implementation of idea and developed first draft of Use Case diagram
4 | 2016-02-25 | 65 | 5 | 72 | 2 | finalized Use Case diagram
5 | 2016-03-03 | 60 | 5 | 68 | 4 | Created sequence diagram
6 | 2016-03-10 | 55 | 5 | 65 | 3 | Data-level sharing
7 | 2016-03-17 | 50 | 5 | 62 | 3 | Visited health center and gathered information on their transfer/exchange process of health data
8 | 2016-03-24 | 45 | 5 | 60 | 2 | finalized our method of transfer/exchange process of health data based on visit
9 | 2016-03-31 | 40 | 5 | 59 | 1 | Splitting the work for the sprints
10 | 2016-04-07 | 35 | 5 | 50 | 9
11 | 2016-04-14 | 30 | 5 | 43 | 7
12 | 2016-04-21 | 25 | 5 | 35 | 8
13 | 2016-04-28 | 20 | 5 | 33 | 2
14 | 2016-05-05 | 15 | 5 | 25 | 8
15 | 2016-05-12 | 10 | 5 | 15 | 10
16 | 2016-05-19 | 5 | 5 | 4 | 11
17 | 2016-05-26 | 0 |  | -20 | 24
Formulas:
Work Date = [Work Date, row above]+7

## Martino N.
Email feature and integration
Week | Work Date | Work Done | Planned Work | Remaining hours | Planned remaining | Description
9 | 2016-03-31 | 2 | 2 | 14 | 14 | Implementing the JavaMail API
10 | 2016-04-07 | 2 | 2 | 12 | 12 | develop simple database connection API
11 | 2016-04-14 | 2 | 2 | 10 | 10 | testing the database connection API
12 | 2016-04-21 | 0 | 2 | 8 | 8
13 | 2016-04-28 | 4 | 2 | 8 | 6 | smtp configuration, creating functions
14 | 2016-05-05 | 4 | 2 | 4 | 4 | testing and fixing bugs
15 | 2016-05-12 | 3 | 2 | 0 | 2 | testing and fixing bugs
16 | 2016-05-19 | 12 | 2 | -3 | 0 | finishing up and writing report
Formulas:
Work Date = [Work Date, row above]+7

## Manisha S.
Encrypting the CCD record
Week | Work Date | Work Done | Planned Work | Remaining hours | Planned remaining | Description
9 | 2016-03-31 | 2 | 2 | 14 | 14 | Research on Encryption
10 | 2016-04-07 | 2 | 2 | 12 | 12 | Implementing AES 128bit encryption
11 | 2016-04-14 | 0 | 2 | 10 | 10
12 | 2016-04-21 | 0 | 2 | 10 | 8
13 | 2016-04-28 | 2 | 2 | 10 | 6 | Modifying existing functions
14 | 2016-05-05 | 2 | 2 | 8 | 4 | Testing and fixing bugs
15 | 2016-05-12 | 2 | 2 | 6 | 2 | Testing and fixing bugs
16 | 2016-05-19 | 2 | 2 | 4 | 0 | Testing and fixing bugs
Formulas:
Work Date = [Work Date, row above]+7

## Nayeem B.
Exporting CCD and integration
Week | Work Date | Work Done | Planned Work | Remaining hours | Planned remaining | Description
9 | 2016-03-31 | 3 | 2 | 14 | 14 | Research on Clinical document architecture
10 | 2016-04-07 | 1 | 2 | 11 | 12 | study mdht library
11 | 2016-04-14 | 4 | 2 | 10 | 10 | write code for generating different parts of the CCD
12 | 2016-04-21 | 2 | 2 | 6 | 8 | integration with openEMR and fixing bugs
13 | 2016-04-28 | 2 | 2 | 4 | 6 | integration with openEMR and fixing bugs
14 | 2016-05-05 | 2 | 2 | 2 | 4 | integration with openEMR and fixing bugs
15 | 2016-05-12 | 4 | 2 | 0 | 2 | integration with openEMR and fixing bugs
16 | 2016-05-19 | 8 | 2 | -4 | 0 | finishing up and writing report
Formulas:
Work Date = [Work Date, row above]+7

## Eric H.
UI/UX
Week | Work Date | Work Done | Planned Work | Remaining hours | Planned remaining | Description
9 | 2016-03-31 | 2 | 2 | 14 | 14 | Sketch rough draft of the UI
10 | 2016-04-07 | 2 | 2 | 12 | 12 | html and css design
11 | 2016-04-14 | 2 | 2 | 10 | 10 | improve and test design
12 | 2016-04-21 | 0 | 2 | 8 | 8
13 | 2016-04-28 | 0 | 2 | 8 | 6
14 | 2016-05-05 | 2 | 2 | 8 | 4 | improve and test design
15 | 2016-05-12 | 2 | 2 | 6 | 2 | improve and test design
16 | 2016-05-19 | 2 | 2 | 4 | 0 | finishing up and writing the report
Formulas:
Work Date = [Work Date, row above]+7